## Sheet1
TEST PLAN
1) Test Plan ID: | BDStall_TP_001
2) Introduction: | It is System Test Plan for online Business System, internet web application, provides access to Authorized users and they can use from anywhere in Bnagladesh.It has two interfaces one is Admin interface another is User interface. Admin can be accesses by BDStall software authorized users, user interface can be accessed by customer and guest. Customers or users can buy any product by created account of this system from Bangladesh. Customers can add their products to the cart and pay online andg can be contacted on mobile number.
3) Test Items: | Admin Interface:User Management, product insert, product update,product delete etc… User Interface: Information of products,smooth navigaqtion, categorization of products, search option for any product, Cart system, contact with product owner,payment system Etc…
4) References: | Requirements, Project Plan , Test Strategy — Use cases (If available) High Level Design doc , Low Level design docs, Process guide line doc, Prototypes
5) Features to be Tested: | a) Admin Interface: 1. User management. *Registration system * login system *logout system *contact system. 2. Product insert. *Insertion of pooduct. 3. Product update. *product update according to price,quantity and date. 4. product delete. *Delete system of products according to quantity b) User Interface: 1) Information of products 2) smooth navigation 3) Categorization of products 4) Search option for any product 5)Cart system 6) contact with owner 7) online payment system ..
6) Features not to be tested: | NA
7) Entry Criteria: | a) Test Design Team formation, Responsibilities, Schedule, Requirements, Test Case Template etc… Training on Domain, on Automation tools b) Test Execution: Readiness of Test Lab Readiness of AUT Requirements Test Case docs Test Data Defect Report Template Etc…
8) Exit Criteria: | All possible test cases executed Maximum defects fixed, Final Regression performed successfully, Confidence on Test process, Time Limitations, Budget Limitations
9) Suspension Criteria: | Show-Stopper bug found, Supplier issues, Vast changes in requirements, If resolving defects are more time consuming/expensive
10) Roles & Responsibilities | Sno Name Role Responsibilities Remarks 1 Ehsanul Alam Sabbir Test Lead Test Planning, guidance, Monitoring and Test control 2 some name, Tester, Test Data Collection, Generating Test Scenarios. 3 some name, Tester, Test Case Documentation, Test execution, defect reporting and tracking for Admin module. 4 some name, Tester, Test Case Documentation, Test execution, defect reporting and tracking for Personal Banking module. 5 some name, Tester, Test Case Documentation, Test execution, defect reporting and tracking for Corporate Banking module
11) Schedule: | Task Days Duration Remarks 1) Understanding & Analyzing Requirements. 7th november Review Meeting 8th november Generating Test Scenarios. 9th novemberJuly Reviews 10th november 5) Test Case Documentation 10th november Reviews 11th november 7) Test Data collection 7th november 8) Reviews 8th november 9) Verifying Test Environment setup (date) 10) Create Test batches (date) 11) Sanity Testing(date) 12) Comprehensive Testing (date) 13) Sanity Testing (date) 14) Selecting Test cases (date) 15) Regression Testing (date) 16) Sanity Testing (date) 17) Selecting Test cases (date) 18) Regression Testing Cycle (date) . . . . . . . . . . 28) Final Regression (date) 29) Evaluating exit criteria (date) 30) Collecting all artifacts (date) 31) Test Summary Report (date) Note: Regression Testing depends on Application and strength of Development team.
12) Training | Training Program on this system Domain Test Automation Training using Selenium Tool
13) Risks & Mitigation | Team member’s issues Vendor issues Time Budget
14) Test Environment / Lab | Application Type: Web Application, Internet and Public Server side: Windows Server 2016 UNIX server Ms Exchange Server a) Web Server, b) EDP, 3) Data storage Bugzilla Tool VSS MS Office Selenium Tool etc…. Browser MS Edge Client side: Windows 10 VSS MS Office Selenium Etc… AUT Environment .NET (C#, VC++, ADO) IIS -web server COM+ -App server SQL Server 2017 for Database server
15) Test Deliverables | Test Plan, Review Reports, RTM Test Scenario docs Test Case docs Test data Opened, Closed Defect Reports Test Summary Report
16) Approvals | Task/s Author /Role Date & Signature 1) Test Plan Documentation Ehsan (Test Lead) 2) Review SomeName (QA Analist) 3) Approval SomeName (Project Manager)
17) Glossary | AUT -Application Under Test . . . PIN -Project Initiation Note . . . SRS- Software Requirements Specification . . .